## 2020-21 WORK PLAN
DER and Inverter-based Resources Subcommittee - Work Plan
Updated: April 21, 2021 | [10 empty] | 2020 |  |  |  | 2021 |  |  |  | 2022
[10 empty] | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec
DER Aggregation / Order 2222 - Active | [11 empty] | Order issued |  | Order 2222-A issued |  |  |  | Compliance filing, ER22-962
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
üBuild Consensus
üFirst Read @ MRC |  |  |  |  | 2012-11-29
üVote at MRC | [5 empty] | 2012-12-20
üVote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01
üProvide Education
üRefine Interests
üDevelop & Refine Design Components | bar: 2012-10-01
üDevelop & Refine Component Options | bar: 2012-10-01 to 2012-12-01
üDevelop & Refine Solution Packages | bar: 2012-11-01 to 2012-12-01
üBuild Consensus | bar: 2013-01-01
üFirst Read @ MRC |  |  |  | 2013-01-01: 2013-01-31
Vote at MRC |  |  |  | 2013-02-01: 2013-02-28
Vote at MC |  |  |  | 2013-02-01: 2013-02-28
FERC Filing |  |  |  | 2013-03-01: 2013-03-01
Hybrid Resources - Phase I - Complete | [17 empty] | FERC filing
Public Distribution Microgrids - Complete
Detailed Work Plan -- Order 2222 Compliance | [9 empty] | DIRS 08.03.2020 | DIRS 09.10.2020 | DIRS 10.02.2020 | DIRS 11.02.2020 | DIRS 11.24.2020 | DIRS 12.07.2020 | DIRS 1.07.2021 | DIRS 1.19.2021 | DIRS 2.03.2021 | DIRS 2.11.2021 | DIRS 3.03.2021 | DIRS 3.15.2021 | DIRS 3.31.2021 | DIRS 4.16.2021 | DIRS 4.27.2021 | DIRS 5.5.2021 | DIRS 5.19.2021 | DIRS 6.11.2021 | DIRS 6.28.2021 | DIRS 7.15.2021 | DIRS 7.23.2021 | DIRS 8.10.2021 | DIRS 8.16.2021 | DIRS 9.14.2021 | DIRS 9.21.2021 | DIRS 10.22.2021 | DIRS 11.22.2021 | DIRS 12.21.2021 | DIRS Jan 2022
Overview of the Order | [11 empty] | X | X
Education | [12 empty] | X | X
Stakeholder Feedback and Discussion | [13 empty] | X | X | X |  | X |  | X |  |  |  |  | X | X |  | X |  | X |  | X | X |  | X | X | X | X
EDC Coordination Workshop - 2 hour meetings | [13 empty] | X |  | X | X | X | X | X | X |  | X |  | X |  | X |  | X |  | X |  |  | X
Straw Proposal Discussion | [21 empty] | X |  | X
Compliance Proposal Development | [25 empty] | X |  | X |  | X |  | X | X |  | X
Compliance Filing - Tariff Review | [35 empty] | X | X | X
Compliance Filing Due Date - Feb 1, 2222 (Pending) | [37 empty] | X
Detailed Work Plan -- Hybrid Resources | [9 empty] | DIRS 08.03.2020 | DIRS 09.10.2020 | DIRS 10.02.2020 | DIRS 11.02.2020 | DIRS 12.07.2020 | DIRS 1.07.2021 | DIRS 2.03.2021 | DIRS 3.03.2021 | DIRS 3.31.2021 | DIRS 4.27.2021 | DIRS 5.19.2021 | DIRS 6.28.2021 | DIRS 7.23.2021
Provide Education | [9 empty] | X | X |  | X |  |  |  |  | X
Document Interests | [10 empty] | X | X
Develop & Refine Design Components | [11 empty] | X | X
Develop & Refine Component Options | [12 empty] | X | X | X | X |  | X
Develop & Refine Solution Packages | [15 empty] | X | X | X | X | X
Build Consensus | [16 empty] | X | X | X | X
Report Recommended Solutions to MIC (& OC) | [19 empty] | X
Detailed Work Plan -- Public Distribution Microgrids | [9 empty] | DIRS 08.03.2020 | DIRS 09.10.2020 | DIRS 10.02.2020 | DIRS 11.02.2020 | DIRS 12.07.2020 | MRC 1.27.2021 | MRC April 2021 | MRC May 2021
Provide Education
Document Interests
Develop & Refine Design Components
Develop & Refine Component Options
Develop & Refine Solution Packages | [9 empty] | X
Build Consensus | [9 empty] | X | X
Report Recommended Solutions to MIC/OC | [10 empty] | X |  | X
Endorsement at MIC/OC | [13 empty] | X
First Read - MRC | [14 empty] | X | X
Endorsement - MRC | [16 empty] | X

## 2022 WORK PLAN
DER and Inverter-based Resources Subcommittee - Work Plan
Updated: March 10, 2022 | [10 empty] | 2020 |  |  |  | 2021 |  |  |  | 2022
Working Items | [9 empty] | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec
DER Aggregation / Order 2222 - Active | [11 empty] | Order issued |  | Order 2222-A issued |  |  |  | Compliance filing, ER22-962
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
üBuild Consensus
üFirst Read @ MRC |  |  |  |  | 2012-11-29
üVote at MRC | [5 empty] | 2012-12-20
üVote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01
üProvide Education
üRefine Interests
üDevelop & Refine Design Components | bar: 2012-10-01
üDevelop & Refine Component Options | bar: 2012-10-01 to 2012-12-01
üDevelop & Refine Solution Packages | bar: 2012-11-01 to 2012-12-01
üBuild Consensus | bar: 2013-01-01
üFirst Read @ MRC |  |  |  | 2013-01-01: 2013-01-31
Vote at MRC |  |  |  | 2013-02-01: 2013-02-28
Vote at MC |  |  |  | 2013-02-01: 2013-02-28
FERC Filing |  |  |  | 2013-03-01: 2013-03-01
Hybrid Resources - Phase I - Complete | [17 empty] | FERC filing
Hybrid Resources - Phase II - Active
Detailed Work Plan -- Order 2222 Compliance | [9 empty] | 1.5.2022 | 1.18.2022 | 2.25.2022 | 3.28.2022 | 4.29.2022 | 5.31.2022 | 6.23.2022 | 7.20.2022 | 8.30.2022 | 9.22.2022 | 10.21.2022 | 11.28.2022 | 12.15.2022
Overview of the Order
Education
Stakeholder Feedback and Discussion
EDC Coordination Workshop - 2 hour meetings
Straw Proposal Discussion
Compliance Proposal Development
Compliance Filing - Tariff Review | [9 empty] | X | X
Compliance Filing Due Date - Feb 1, 2222 | [10 empty] | X
Implementation Discussions (see separate Order 2222 work plan for more detail) | [11 empty] | X | X | X | X | X | X | X | X | X | X | X
Detailed Work Plan -- Hybrid Resources - Phase II | [12 empty] | 3.28.2022 | 4.29.2022 | 5.31.2022 | 6.23.2022 | 7.20.2022 | 8.30.2022 | 9.22.2022 | 10.21.2022 | 11.28.2022 | 12.15.2022
Provide Education | [12 empty] | X
Document Interests | [12 empty] | X
Develop & Refine Design Components | [12 empty] | X
Develop & Refine Component Options
Develop & Refine Solution Packages
Build Consensus
Report Recommended Solutions to MIC (& OC)