## Sheet1
Interconnection Process Reform Work Plan | Meeting
| 2021-04-23 | 2021-06-01 | 2021-06-29 | 2021-07-19 | 2021-08-23 | 2021-09-20 | 2021-10-07 | 2021-10-19 | 2021-10-29 | 2021-11-04 | 2021-11-18 | 2021-11-30 | 2021-12-07 | 2021-12-14 | 1//2022 | 1st week March '22 | 2nd week March '22 | 3//2022 | 4//2022
Charter Development & Approval | bar: 2021-04-23
Develop Work Plan | bar: 2021-04-23
Education & Joint Fact-Finding | bar: 2021-04-23
Interest Identification | bar: 2021-04-23 to 2021-06-01
Develop Design Components | bar: 2021-06-01 to 2021-06-29
Document Relative Importance of each Component | bar: 2021-06-01 to 2021-06-29
Develop Options for each Component | bar: 2021-06-29 to 2021-07-19
Narrow Options | bar: 2021-07-19 to 2021-08-23
Develop Packages | bar: 2021-07-19 to 2021-08-23
Narrow Packages | bar: 2021-09-20 to 2021-11-18
(Compare Packages to Interests
& Importance Ratings)
Consensus Testing / Polling | bar: 2021-10-19; 2021-11-18 to 2021-11-30
Tier 1 Decision Making | bar: 2021-11-30 to 2021-12-07
First Read PC | bar: 2021-12-14
Endorsement PC | [14 empty] | X
Review OATT Language with IPRTF | [15 empty] | X
Review OATT Language with IPRTF | [16 empty] | X
First Read MRC | [17 empty] | X
Endorsement MRC | [18 empty] | X
Endorsement MC | [18 empty] | X