## Sheet1
DRAFT - 2019 Market Efficiency Process Enhancement Task Force (MEPETF) Phase 2 Work Plan
Topic | 2019-01-25 | 2019-02-01 | 2019-02-08 | 2019-02-28 | 2019-03-07 | 2019-03-21 | 2019-04-25 | 2019-05-01 | 11/01/19 or 12/01/19
Develop & Refine Solution Packages | X
Stakeholders Provide Additional Packages to Facilitation Team for Posting | bar: 2019-02-01
Build Consensus | X | bar: 2019-02-08
Package Strawman Poll | bar: 2019-02-08
Review Strawman Poll | bar: 2019-02-28
Tier 1 Decision Making | bar: 2019-02-28
Report to PC | bar: 2019-03-07
1st Read MRC | bar: 2019-03-21
2nd Read MRC | bar: 2019-04-25
Report to MC | bar: 2019-04-25
Finalize and submit FERC Filing | bar: 2019-05-01
Receive FERC direction and implement changes | [8 empty] | X