## Setup (hidden)
Enter Stakeholder Group Name in cell A2:
Phase Angle Regulator Task Force
Enter issue title (use title from Issue Tracking if applicable) in cell A5:
PARs as Controllable A.C. Merchant Transmission Facilities

## Workplan
2015 Phase Angle Regulator Task Force
Updated: May 13, 2015
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
üBuild Consensus
üFirst Read @ MRC |  |  |  |  | 2012-11-29
üVote at MRC | [5 empty] | 2012-12-20
üVote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01
üProvide Education
üRefine Interests
üDevelop & Refine Design Components
üDevelop & Refine Component Options
üDevelop & Refine Solution Packages
üBuild Consensus
üFirst Read @ MRC | [6 empty] | 2013-01-31
Vote at MRC | [7 empty] | 2013-02-28
Vote at MC | [7 empty] | 2013-02-28
FERC Filing | [8 empty] | 2013-03-01
OVERVIEW | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | Mar. 2013 | 2014-12-01 | 2015-03-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01
Phase Angle Regulator Transmission Injection and Withdrawal Rights | [9 empty] | Education |  | Interests & Design Components | Solution Options & Packages |  | Narrow packages / Decision making | Tariff Language / Manual Language | Recommendation to PC | PC/MRC Voting
Topic | [9 empty] | 2014-12-17 | 2015-03-27 | 2015-05-14 | 2015-06-12 | July | July | August | September
Charter Development & Approval | bar: 2014-12-01
Develop Work Plan | bar: 2015-05-01
Education and Fact-finding | bar: 2014-12-01 to 2015-03-01
Interest Identification | bar: 2015-05-01
Develop Design Components | bar: 2015-05-01 to 2015-06-01
Document Relatative Importance of each component | bar: 2015-06-01
Develop Options for each Component | bar: 2015-06-01 to 2015-08-01
Narrow Options | bar: 2015-07-01 to 2015-08-01
Develop Packages | bar: 2015-08-01
Narrow Packages (Compare Packages to Interests & Importance Ratings) | bar: 2015-09-01
Consensus Testing | bar: 2015-09-01
Tier 1/Tier 2 Decision Making | bar: 2015-09-01 to 2015-10-01
Reporting | bar: 2015-10-01

## 1. Interest Identification
Phase Angle Regulator Task Force
PARs as Controllable A.C. Merchant Transmission Facilities
Interest Identification
Instructions: List interests of all parties on this page.
1 | Establish whether PAR technology has appropriate controllability. Namely, the ability to set power flows and have the facility hold those flows, the ability to reverse flows, and the ability to zero flows (stop the transfer).
2 | Identifying efficient solutions to seams issues
3 | Reliability should be maintained
4 | Outcomes should be non-discriminatory. Keep in mind that 'comparability' does not mean 'identical'.
5 | Consideration of the surrounding facility owners with regards to the PAR installation location during the System Impact Study evaluation.
6 | Understanding the system transfer impacts of a new PAR controlled facility as well as the flow on the individual facility
7 | Identifying whether rights on a PAR controlled facility would be subject to continuing operational rule requirements or whether they would be set during the study.
8 | Account for impacts on existing topology and operations including existing PARs with respect to granting new rights
9 | Understand how neighboring systems evaluate and grant rights
10
11
12
13
14
15

## 2. Options Matrix- Design Comp.
Phase Angle Regulator Task Force
PARs as Controllable A.C. Merchant Transmission Facilities
OPTIONS MATRIX
Strive for simplicity
Solution Options2
# | Design Components related to PAR-specific merchant transmission facilities1 | Priority | Status Quo | A (PJM proposal) | B | C | D | E
1 | Number and Frequency of tap changes |  |  | Customer design concern. PJM will require controllability consistent with design component #12 and without regard to the number or frequency of tap changes this will require.
2 | Precision of flow control |  |  | Consistent with existing requirements in Manual 11 related to allowable deviations for all resources which are self scheduled. Deviations governed by existing rules for assessing Operating Reserve Charges.
3 | Capabilities of establishing flow control over a range of system conditions. |  |  | Customer to design the facility such that it maintains the ability to control flows across the range of requested MWs under all required contingency conditions (e.g. All PJM RTEP planning requirements).
4 | Interface transfer capability |  |  | 1. Test to determine capability of proposed equipment 2. Test to determine impact on existing rights holders
5 | Rights Determination |  |  | Customer requests rights. Studies to determine system impacts based on granting rights as with other types of facilities (e.g. HVDC & VFT). Minimum of: 1. Load flow (Generation deliverability/Load deliverability/N-1-1) 2. Short circuit 3. Stability |  |  |  |  | Low
6 | Loss of Rights |  |  | Customer unable to demonstrate ability to flow scheduled service |  |  |  |  | Low - Medium
7 | PAR Controllability - Achieving zero flow |  |  | Customer must be able to achieve zero flow (stop flow) when directed by PJM. If unable to achieve zero flow, PJM reserves the right to disconnect the PAR to prevent unscheduled flows. |  |  |  |  | Low - High
8 | Step size (MW) |  |  | Acceptable step size will be studied based on the proposed location for interconnection of each facility on a case by case basis to determine impacts; however, steps of 20 MW steps or less are expected to be acceptable in most applications. New language required in Manual 14E.
9 | Initial flow quantity from a zero flow position (MWs) |  |  | Initial energization to achieve a MW flow from a zero flow position shall not exceed the established step size for the facility as determined in design component #8. This may be relaxed or tightened if local system is unable to sustain events of this magnitude without impact to other parties. New language required in Manual 14E. |  |  |  |  | Medium
10 | Interim rights |  |  | Customer is able to obtain interim rights through the interim deliverability process currently outlined in PJM Manual 14A. |  |  |  |  | Medium - High
11 | Cost allocation for future baselines |  |  | Consistent with treatment of HVDC and VFT facilities |  |  |  |  | High
12 | Facility control |  |  | Automatic control required with ability to manually adjust
Instructions:
1Design Components - each is an "attribute" or "component" of any proposed solution. Consensus of the group should be sought on selection of a set of solution criteria.
2Solution Options - each is a solution alternative elicited from the stakeholder group that meet one of the specific solution criteria.
To complete the matrix:
1. Elicit from the stakeholder group a set of components (attributes) desired for any proposed solution. Enter a short label for each in the Design Components column.
2. If needed, enter a more detailed description of each criteria on the "Component Details" tab.
3. Using informal/non-binding voting, rate each component's priority in the final solution as "high/medium/low"
4. Elicit from the stakeholder group potential solution alternative(s) for each component. Enter a short label for each in the Solution Options columns.
5. If needed, enter a more detailed description of each potential solution option on the "Solution Details" tab.
6. Once the matrix is filled out, the group will attempt to select a single solution alternative (column) for each component (row) to form a solution "package".
Example: cells 1B, 2C, 3A, 4B, 5D could make up a solution package.
7. If consensus is achieved on a single package (Tier 1 decision-making method), this will be documented in a Consensus Proposal Report to the parent committee.
8. If not, the group will identify up to 3 possible solution packages in a comparative Proposal Alternatives Report to the parent committee (Tier 2 decision-making method).

## 2a. Component Details
Phase Angle Regulator Task Force
PARs as Controllable A.C. Merchant Transmission Facilities
COMPONENT DETAILS
Instructions: Complete this form as needed. Design components should be populated from the Options Matrix.
Design Component |  | Detailed Description
1 |  | <enter detailed description of this component>
2 |  | <enter detailed description of this component>
3 |  | <enter detailed description of this component>
4 |  | <enter detailed description of this component>
5 |  | <enter detailed description of this component>

## 2b. Solution Details
Phase Angle Regulator Task Force
PARs as Controllable A.C. Merchant Transmission Facilities
SOLUTION DETAILS
Instructions: Complete this form as needed. Potential solutions should be populated from the Proposal Matrix
Package Solutions2
| A | B | C | D | E
1
2
3
4
5

## 3. Package Matrix
Phase Angle Regulator Task Force
PARs as Controllable A.C. Merchant Transmission Facilities
PACKAGE/ PROPOSAL MATRIX
Instructions:
1. Copy over design component, priority, and status quo columns from options matrix
2. Complete individual packages in columns by selecting individual component options from the options matrix.
Packages
# | Design Components | Priority | Status Quo | A | B | C | D | E
1
2
3
4
5
6
7
8
9 | [8 empty] | Low
10 | [8 empty] | Low - Medium
Low - High
Medium
Medium - High
High

## 4. Parking Lot
Phase Angle Regulator Task Force
PARs as Controllable A.C. Merchant Transmission Facilities
Interest Identification
Instructions: Use this space to document any items not specific to another topic area.
Item # | Description | Response
1 | Compare and contrast AC Phase Angle Regulator (phase shifting transformer) technology and DC controllable transmission in a table. | See Tab 5 below
2 | Will cost allocation be discussed in the PARTF | No. Cost allocation will be handled per the current PJM tariff and is out of scope for consideration by the PARTF.
3 | Education request: better understanding of interconnections studies and system impacts associated with PAR technology and the studies/impact on neighboring systems | Education presented on 6/12
4 | How does slight inaccuracy of PAR flows (e.g. ~3%), in bulk aggregate and over time, impact the system?
5 | Question about how a bypass installed with a PAR would affect the ability to receive ATC rights while in bypass in lieu of TIRs/TWRs . | It was decided that this question was not within the scope of the PAR TF and would be reported to the PC as a sidebar question that arose.
6
7
8

## 5. AC_DC Comparison
COMPARISON BETWEEN CAPABILITIES OF PAR TECHNOLOGY AND DIRECT CURRENT TECHNOLOGY
CHARACTERISTICS | PHASE ANGLE REGULATORS (PAR) | DIRECT CURRENT (DC) | Variable Frequency Transformer (VFT)
Flow Control Capability | PARs technology can reliability control power flows in a single direction or bi-directionally, provided that the magnitude of the induced phase angle is sufficient to address the system conditions encountered at the source. Generally available equipment have phase angles capabilities between +-20 and +-60 degrees depending on the PAR size. A 550 MVA unit would have up to 50 degrees of regulation in 32 steps. Capable of providing reliable bidirectional power flows, provided that size of equipment and phase angle “range” are adequate | Power flow capability that can be designed as a unidirectional or bidirectional system | Power flow capability that can be designed as a unidirectional or bidirectional system
Precision | The level of precision will vary depending on the size of the facilities and the number of degrees. Flows can generally be calibrated within 3-4% of desired target flow | Flows can be controlled to levels very close to target flow | Flows can be controlled to levels very close to target flow
Availability | The number of available “tap changes” on modern PARs facilities can be between 750,000 and 1.2 million operations, depending on loading during tap changes, which would allow 50-80 “tap changes” per day over a 40 year useful life. Inspections are required on a 2 to 3 year cycle. | DC equipment must be taken out of service for several days to one week per year for maintenance Generally provides control of flow somewhat independent of the condition of the surrounding grid. | Manufacturer indicates lower maintenance requirements as compared to HVDC
Set Point After N-1 |  | HVDC remains as set after most N-1 events | Flows can be controlled to levels very close to target flow

## Revision History
Phase Angle Regulator Task Force
PARs as Controllable A.C. Merchant Transmission Facilities
Revision History
Current Spreadsheet Version:
Version | Posting Date | Description of changes
1
2
3